## Sprint Plan
Sprint | Task ID | Task Name | Description | Owner | Start Week | End Week | Status | Remarks
Sprint 1 | T1 | Data Collection | Collect Azure storage usage dataset | Nune Sai Shiva Prem | Week 1 | Week 1 | Completed | Dataset prepared
Sprint 1 | T2 | Data Cleaning | Handle missing values and normalize dataset | Nune Sai Shiva Prem | Week 1 | Week 2 | Completed | Clean dataset created
Sprint 1 | T3 | Data Validation | Verify dataset structure and consistency | Nune Sai Shiva Prem | Week 2 | Week 2 | Completed | Ready for feature engineering
Sprint 2 | T4 | Feature Engineering | Create lag variables and derived features | Nune Sai Shiva Prem | Week 3 | Week 3 | Completed | Lag features added
Sprint 2 | T5 | Trend Analysis | Generate rolling averages and seasonality flags | Nune Sai Shiva Prem | Week 3 | Week 4 | Completed | Trend indicators created
Sprint 2 | T6 | Data Wrangling | Prepare dataset for ML models | Nune Sai Shiva Prem | Week 4 | Week 4 | Completed | Model-ready dataset
Sprint 3 | T7 | Model Training | Train Linear Regression, XGBoost and ARIMA models | Nune Sai Shiva Prem | Week 5 | Week 5 | Completed | Models trained
Sprint 3 | T8 | Model Evaluation | Evaluate models using MAE and RMSE | Nune Sai Shiva Prem | Week 5 | Week 6 | Completed | Best model selected
Sprint 3 | T9 | Hyperparameter Tuning | Optimize XGBoost parameters | Nune Sai Shiva Prem | Week 6 | Week 6 | Completed | Performance improved
Sprint 3 | T10 | Backtesting | Validate forecasting robustness | Nune Sai Shiva Prem | Week 6 | Week 6 | Completed | Stable model achieved
Sprint 3 | T11 | Prediction Pipeline | Generate demand predictions using trained model | Nune Sai Shiva Prem | Week 6 | Week 6 | Completed | Predictions saved